## Sheet1
Task | Tanggal Mulai | Tanggal Selesai | Status | Nama Developer | Task | Pengerjaan
Pre processing | 2021-10-20 | 2021-10-24 | Done | Annisaa | Pre processing | Modul 1
Modelling | 2021-10-24 | 2021-10-30 | Done | Riska | Modelling | Modul 2
Augmentasi | 2021-10-30 | 2021-11-10 | Ongoing | Annisaa | Augmentasi | Modul 3
Oversampling/Downsampling | 2021-11-10 | 2021-11-24 | Waiting | Riska | Oversampling/Downsampling | Modul 4
Pretrained Model | 2021-11-24 | 2021-12-08 | Waiting | Annisaa | Pretrained Model | Modul 5
Deployment | 2021-12-08 | 2021-12-22 | Waiting | Riska | Deployment | Modul 6